# Securafy Certification & Compliance Matrix

Prepared for the $2M → $10M growth plan · July 2026

Compliance facts verified against current sources as of 2026-07-07 (see Sources). CMMC/CJIS/HIPAA move fast — re-verify anything you attest to, and confirm state-specific CJIS rules with your CSA.

# Purpose

This document maps the certifications and compliance capabilities Securafy needs — to each seat, each service line, and each of the three vertical campaigns (Chamber of Commerce, CJIS, Healthcare) — and ranks them by acquisition priority. It is the bridge between the job descriptions (which name the certs per role) and the timeline (which sequences when they are acquired).

# Regulatory key dates (verified 2026-07-07)

| Date | What happens | Affects |
| --- | --- | --- |
| Dec 16, 2024 | CMMC 32 CFR program rule effective | CMMC |
| Oct 1, 2024 | CJIS MFA / advanced authentication mandatory & audited (already in force) | CJIS |
| Dec 27, 2024 | CJIS Security Policy v6.0 released (rebuilt on NIST 800-53 Rev 5) | CJIS |
| Nov 10, 2025 | CMMC 48 CFR / DFARS rule effective — CMMC now enters DoD contracts (Phase 1: L1/L2 self-assessment) | CMMC |
| Sep 21, 2026 | FIPS 140-2 validations go "historical" — must migrate to FIPS 140-3 | CJIS (and any FIPS-crypto) |
| Nov 10, 2026 | CMMC Phase 2 — Level 2 C3PAO third-party certification broadly required for CUI contracts | CMMC |
| Oct 1, 2027 | CJIS P2–P4 controls fully auditable/sanctionable | CJIS |
| Nov 10, 2027 / 2028 | CMMC Phase 3 (Level 3) / Phase 4 (full implementation) | CMMC |
| Dec 1, 2026 | ISC2 HCISPP credential sunsets → CHPS becomes the default healthcare privacy/security cert | Healthcare |
| Status: proposed | HIPAA Security Rule NPRM (pub. Jan 6, 2025) — still NOT finalized as of mid-2026 | Healthcare |

# 1. Priority individual certifications — get ASAP

| Cert | Body | Seat / Person | Why it matters | Effort | Priority |
| --- | --- | --- | --- | --- | --- |
| CISM | ISACA | vCISO (Rodney) | Governance/management credibility; anchors the MSSP + vCISO practice | ~5 yrs security-mgmt experience + exam | P0 |
| CISSP | ISC2 | vCISO (Rodney) | Broad security-leadership credential; table stakes for a vCISO offering | ~5 yrs experience (or 4 + degree) + exam | P0 |

Sequencing reality: Rodney is slated to hold both vCIO and vCISO. Studying for CISM + CISSP takes real hours he does not have while still buried in reactive/vCIO delivery. This reinforces the plan's core move — offload Rodney's reactive and TAM work first (stand up the TAM + Support Desk cutover) so he has the bandwidth to earn these certs and run TBRs. The certs and the seat-split are the same problem.

# 2. Certification-to-seat matrix

| Seat | Required | Recommended / Growth |
| --- | --- | --- |
| vCIO (Rodney) | vCIO/TBR methodology proficiency | ITIL Foundation; business/financial-planning credentials |
| vCISO (Rodney) | CISM, CISSP | CCP (CMMC), CRISC, CISA; CHPS (AHIMA, healthcare) |
| Technology Alignment Manager | CompTIA A+, Network+, Security+ | Cloud+, Server+; Microsoft M365 fundamentals |
| Support Desk Manager (Brandon) | ITIL Foundation (recommended) | Service-management / vendor-management credential |
| Design Desk Engineer | Microsoft product fundamentals | CompTIA Network+/Server+; vendor procurement certs |
| Centralized Services Engineer (Ralph Reyes) | Holds: M365 Enterprise Administrator Expert, Teams Admin (MS-700), AZ-900, MS-900, SC-900, CCNA 1–4 | CompTIA Cloud+/Server+ (optional) |
| Systems Engineer & Security Specialist (L3) | A+, Network+, Server+, Cloud+, Security+ (per existing JD) | Microsoft/Azure |
| Senior Systems Engineer & Security Expert (L4) | above + PenTest+, CASP+ (per existing JD) | Vendor security certs |

# 3. Compliance frameworks & the three vertical campaigns

Owner for all three: vCISO (Rodney), supported by the L3/L4 security engineers.

## ⚠️ Offshore access boundary (applies across CJIS, CMMC, and some healthcare)

Reyes (Centralized Services) is in the Philippines, and the outsourced Mission Control desk may include non-US staff. CJIS bars offshore/foreign-national access to CJI; CMMC restricts non-US-person access to CUI/SPD. Design control: segment clients into regulated vs general; give regulated clients a US-staffed delivery lane end-to-end (help desk + centralized services + engineering by US, background-checked staff); wall Reyes and any offshore/outsourced staff off from regulated environments via RMM/PSA client-group segregation; Mission Control (confirmed) can supply a dedicated US-based, background-checked help-desk queue for regulated clients — those staff also need the CJIS Security Addendum + awareness training. Document and audit the boundary in the CJIS and CMMC packages. This is an audit-failing item if left implicit.

## CMMC — (active client already; currently unowned) — the rule is now LIVE

Standard: NIST SP 800-171 Rev 2 underpins Level 2 (all 110 controls / 320 objectives). Level 1 (FCI) = annual self-assessment + affirmation. Level 2 (CUI) = self-assessment OR C3PAO assessment depending on the contract, triennial + annual affirmation. Level 3 (Expert) = government-led DIBCAC assessment of additional 800-172 controls, and requires Level 2 C3PAO first. (NIST 800-171 Rev 3 exists but CMMC L2 is still pegged to Rev 2 — watch for future DoD adoption.)

Rule status (corrected): the 48 CFR / DFARS rule is effective as of Nov 10, 2025 — CMMC is no longer "pending," it is entering DoD contracts on a 4-phase ramp. Nov 10, 2026 (Phase 2) is the key near-term date when Level 2 third-party (C3PAO) certification becomes broadly required. C3PAO assessor capacity is constrained — clients should get in the queue now, which is the market opening for readiness/advisory work.

Securafy's path: register as a Registered Provider Organization (RPO) with the Cyber AB and staff RP → RPA (advisory) and/or CCP (certification) credentials. (Note: as of ~April 2026 ISACA administers the CMMC assessor/professional exams — CCP/CCA/LCCA — via the CAICO function.)

Independence rule (confirmed): a C3PAO cannot both consult/remediate and assess the same client (≈36-month separation). An advisory MSP operating as an RPO is on the clean side — you do readiness/remediation and hand assessment to an independent C3PAO. Do not pursue C3PAO status for clients you remediate.

Does Securafy itself need CMMC? (nuance): not an automatic standalone cert. If CUI or Security Protection Data flows to Securafy, Securafy's services are pulled into each client's assessment scope. For a multi-client DIB MSP, getting its own Level 2 assessment is strongly recommended (turns N client audits into one, and is a differentiator) but not universally mandated. (A cloud service touching CUI is a different bar — FedRAMP Moderate under DFARS 7012.)

First move: assign the existing CMMC client to the vCISO seat and align that engagement to 800-171 Rev 2 with a documented POA&M.

## CJIS — (law-enforcement / government vertical)

Basis: FBI CJIS Security Policy v6.0 (released Dec 27, 2024), now fully rebuilt on NIST SP 800-53 Rev 5 (Moderate baseline), ~20 policy areas. There is no company "CJIS certification" — compliance is adherence + audit by your state CJIS Systems Agency (CSA). (v6.1 expected in 2026; treat CJIS as a moving target.)

Obligations for a vendor touching Criminal Justice Information (CJI): sign the CJIS Security Addendum (per agency + personnel certifications); fingerprint-based background checks for all staff with CJI access (renewal cadence is CSA-driven, not a fixed 2-year federal rule; no foreign-national/offshore access); CJIS Security Awareness Training within 6 months then ANNUALLY (corrected — it is yearly, not biennial), role-based; MFA is already mandatory (since Oct 1, 2024) on all CJI access paths incl. RMM/remote admin; FIPS-validated encryption in transit, at rest, and (new in v6.0) during processing; audit logging, incident response, media protection.

Watch item: migrate any FIPS 140-2 crypto to FIPS 140-3 before Sep 21, 2026; P2–P4 controls fully auditable Oct 1, 2027.

Owner deliverable: a CJIS compliance package the vCISO can attest to and sell as a differentiator for the government motion.

## Healthcare — (HIPAA)

Basis: HIPAA Security Rule, Privacy Rule, and Breach Notification Rule. An MSP handling PHI is a business associate and needs a BAA with every covered-entity client, flowed down to any subcontractors touching PHI. Breach notification to the covered entity is required within 60 days of discovery.

Security Rule NPRM (corrected status): the proposed modernization (published Jan 6, 2025) is still PROPOSED — not finalized as of mid-2026 (missed its spring-2026 target; 4,700+ comments; active withdrawal pressure; uncertain outcome). Do not build the program as if it's law — but its likely mandates (mandatory MFA, encryption at rest + in transit, asset inventory/network map, annual pen testing, removal of the "addressable" vs. "required" distinction) are best practice anyway, so position for them.

No government "HIPAA certification" exists — compliance is self-attested, supported (not replaced) by HITRUST CSF (org-level, current v11.x; tiers e1/i1/r2) or SOC 2 + HIPAA mapping. Never advertise "HIPAA certified" — say "HIPAA-aligned."

Individual credential: CHPS (AHIMA) is the authoritative, portable one (and becomes the default when ISC2 sunsets HCISPP on Dec 1, 2026). CHPSE is a different, less-recognized private-vendor credential — not an AHIMA "senior CHPS"; don't conflate them.

Owner deliverable: a HIPAA-aligned compliance offering (BAA, documented annual Security Risk Analysis, safeguards, breach readiness) owned by the vCISO.

| Vertical | Framework / standard | Org-level | Individual credential | Key obligation |
| --- | --- | --- | --- | --- |
| CMMC | NIST 800-171 Rev 2 / CMMC L1–L3 | RPO (not C3PAO) | CCP, RP/RPA | 800-171 controls + POA&M; own L2 assessment recommended |
| CJIS | CJIS Sec. Policy v6.0 (NIST 800-53 R5) | Security Addendum signed | CJIS annual awareness training | Background checks, MFA, FIPS 140-3 encryption |
| Healthcare | HIPAA Security/Privacy Rules | HITRUST CSF (optional) | CHPS (AHIMA) | BAA + annual risk analysis + safeguards |

# 4. Service-line certifications

| Service line | Org-level partner/designation | Individual certs | Notes |
| --- | --- | --- | --- |
| Core MSP / MSSP | Microsoft Solutions Partner | CompTIA ladder + Microsoft | Foundation for everything else |
| AI as a Service | Microsoft (Azure AI) partner | Azure AI Engineer (AI-102); Microsoft Applied Skills (AI/Copilot) | Emerging — certs still maturing; prioritize hands-on capability |
| SharePoint as a Service | Microsoft Solutions Partner — Modern Work | Microsoft 365 Administrator (MS-102) | CERT-READY NOW: Ralph Reyes holds M365 Enterprise Administrator Expert — no cert gap; launch-ready |
| Website as a Service | — (skill/tool-based) | Vendor tool training for the AI website stack | No formal certification path; competency-based |
| AI University | — | Train-the-trainer / instructional design | Internal enablement, not cert-gated |

# 5. Current holdings & gaps

Current cert holders (confirmed — full detail in `11-staff-certification-inventory.xlsx`):

Ralph Reyes (Centralized Services, PH): M365 Enterprise Administrator Expert, Teams (MS-700), AZ-900, MS-900, SC-900, CCNA 1–4. Strongest profile; SharePoint-aaS ready.

Tom Bak (onsite tech, US): CompTIA A+ & Network+ (legacy 2010), MCP, MS Configuring Windows Devices (exam 70-697 — retired).

Justin Swickard (onsite tech, US): CompTIA A+, associate's degree (Zane State).

Nobody currently holds CISM, CISSP, or any CMMC/CJIS/security-governance credential — the entire governance tier is still to acquire (P0).

Technician bench gap: the two US onsite techs (Tom, Justin) have no current security/cloud certs. The MSSP + CMMC/CJIS/Healthcare strategy needs Security+ (and CompTIA CE renewal) + modern Microsoft/Azure certs on them (P1–P2). Upside: being US-based, they are eligible for regulated-client work with a background check.

Biggest gaps today:

Governance tier (CISM/CISSP): no seat holds them — the vCISO practice has no credential floor.

CMMC role designations (RPO/RP/CCP): none — the existing CMMC client is unowned and un-credentialed, with the Nov 10, 2026 C3PAO deadline approaching.

CJIS / HIPAA formal capability: none documented; CJIS MFA + FIPS 140-3 + annual training must be provably in place.

Service-line certs: Ralph Reyes holds M365 Enterprise Administrator Expert — SharePoint-aaS is cert-ready now. AIaaS: he has Azure Fundamentals (AZ-900) but needs Azure AI (AI-102) for deep AI delivery — the one service-line cert gap to close.

Offshore access boundary: must be designed and documented before onboarding CJIS/CMMC clients at scale (see the boundary note in Section 3).

# 6. Acquisition priority (feeds the timeline)

| Window | Certifications / capabilities | Rationale |
| --- | --- | --- |
| P0 — 0–6 months | CISM + CISSP (Rodney); CMMC RPO registration + RP; assign & scope the CMMC client (800-171 Rev 2 + POA&M); CJIS baseline (annual awareness training, MFA, background checks, FIPS 140-3 migration before Sep 21, 2026) | Unblocks the MSSP/vCISO practice; secures the existing CMMC client ahead of Nov 10, 2026; clears the nearest hard deadline (FIPS) |
| P1 — 6–18 months | CCP (CMMC, via ISACA); HIPAA-aligned offering (BAA + annual risk analysis + safeguards); TAM CompTIA (Security+, Network+); Microsoft MS-102 for SharePoint-aaS; evaluate Securafy's own CMMC L2 assessment | Builds the vertical campaigns and the first new service line; positions for CMMC Phase 2 |
| P2 — 18–48 months | CASP+/PenTest+ depth; Azure AI (AI-102) for AIaaS; HITRUST if Healthcare scales; CRISC/CISA and CHPS for GRC depth | Scales the offerings as revenue and headcount grow |

# 7. Assumptions & items to verify

Rodney fills the combined vCIO + vCISO seat (per Randy, 2026-07-07).

Current cert holders are unknown — confirm before finalizing the timeline (may accelerate several items).

State-specific CJIS rules can be stricter than the federal policy — confirm with your CSA before attesting.

The HIPAA Security Rule NPRM is not law — monitor the Federal Register/OCR for a final rule, narrowing, or withdrawal.

Exam/registration costs and study time are not yet quantified — can be added as a budget annex.

# Sources (verified 2026-07-07)

CMMC: [Cyber AB — Ecosystem Roles](https://cyberab.org/CMMC-Ecosystem/Ecosystem-roles) · [Acquisition.gov — DFARS 252.204-7021](https://www.acquisition.gov/dfars/252.204-7021-contractor-compliance-cybersecurity-maturity-model-certification-level-requirements.) · [DoD CIO — CMMC Level 2 Assessment Guide](https://dodcio.defense.gov/Portals/0/Documents/CMMC/AssessmentGuideL2v2.pdf) · [DoD CIO — ESP/MSP scoping](https://dodcio.defense.gov/Portals/0/Documents/CMMC/TechImplementationCMMC-Rqrmnts.pdf) · [Summit 7 — 48 CFR final rule](https://summit7.us/blog/final-rule-update-48-cfr-and-the-cmmc) · [ConnectWise — CMMC final rule for MSPs](https://www.connectwise.com/blog/cmmc-final-rule) · [PreVeil — Does your MSP need CMMC](https://www.preveil.com/blog/when-does-your-msp-need-to-be-cmmc-compliant/)

CJIS: [FBI CJIS file repository](https://www.fbi.gov/file-repository/cjis) · [CJIS Security Policy v6.0 (2024-12-27)](https://le.fbi.gov/file-repository/cjis_security_policy_v6-0_20241227.pdf) · [Microsoft Learn — CJIS offering](https://learn.microsoft.com/en-us/compliance/regulatory/offering-cjis) · [Entrust — CJIS MFA mandate](https://www.entrust.com/blog/2024/08/understanding-the-new-cjis-mfa-mandate-and-its-importance-for-your-agency) · [Datto — FIPS 140-3 for MSPs](https://www.datto.com/blog/fips-140-3/) · [NuHarbor — 2026 CJIS checklist](https://www.nuharborsecurity.com/blog/cjis-compliance-requirements-the-2025-checklist-for-state-local-agencies)

HIPAA: [HHS/OCR — Security Rule NPRM fact sheet](https://www.hhs.gov/hipaa/for-professionals/security/hipaa-security-rule-nprm/factsheet/index.html) · [HIPAA Journal — Security Rule update status (Mar 2026)](https://www.hipaajournal.com/final-rule-implementing-hipaa-security-rule-updates-edges-closer/) · [HIPAA Journal — BA compliance](https://www.hipaajournal.com/hipaa-compliance-for-business-associates/) · [HITRUST — Framework (CSF)](https://hitrustalliance.net/hitrust-framework) · [AHIMA — CHPS](https://www.ahima.org/certification-careers/certification-exams/chps/)