# Securafy 4-Year Hiring & Certification Timeline

The revenue-gated roadmap from $2M to $10M · 2026 → 2030

Prepared July 2026 · EOS-aligned (4-Year Target → Annual Plans → Quarterly Rocks)

# The core logic: revenue-gated and self-funding

The constraint on Securafy's growth is revenue, not capacity — Securafy can add ~1,000 managed seats per year without strain. That means this roadmap is not "hire people and add clients." It is a self-funding sequence: the seats that generate revenue are stood up first, and the non-recurring revenue (NRR) and protected renewals they produce fund the next wave of hires and certifications.

The whole plan pivots on one move: offload Rodney. Today Rodney is the Integrator and the vCIO and the vCISO and absorbs reactive work — so the revenue engine (the Technology Business Reviews) never runs. Free that seat, restart the TBRs, and the revenue that follows pays for everything downstream.

The self-funding chain:

Stand up TAM + Mission Control (offload Rodney) → Rodney runs TBRs → TBRs drive NRR + renewals → revenue funds Design Desk + Centralized Services + certs → compliance/MSSP + new service lines → revenue funds delivery pods → $10M.

Revenue is now modeled in two divisional P&Ls (04-financial-model.xlsx): Core MSP/MSSP anchored on your PLANNED model ($2.30M → $5.73M, 2026–28, extended to 2030) and Securafy Digital Services layered on top, rolling up to the $10M target. The Core MSP plan is aggressive — it assumes +$10–15K/mo net-new MRR (vs. current actual <$6K) and no churn — so stress-test it with lower growth.

# 4-Year Target (2030)

~$10M revenue, up from ~$2M — a healthier mix of MRR, NRR (target 20–30% of MRR), and compliance/MSSP premium.

Full target Accountability Chart staffed: Rodney is a pure Integrator; vCIO and vCISO are separate seats; multiple vCIO+TAM delivery pods; Finance/Admin off Randy's plate.

Five service lines live (AIaaS, SharePoint-aaS, Website-aaS, AI University, core MSP/MSSP) and three vertical campaigns producing (Chamber, CJIS, Healthcare).

Securafy positioned as a compliance-forward MSSP: CMMC RPO, CJIS-capable, HIPAA-aligned.

# Near-term Rocks — Q3 2026 (now, Jul–Sep)

These are the 90-day priorities. Everything else waits behind them.

| Rock | Owner | Done when |
| --- | --- | --- |
| #1 — Restart the TBR engine | Rodney (vCIO) | TBRs scheduled a year out; monthly TBRs running for larger clients; roadmap+budget produced per client |
| Mission Control full cutover | Brandon (Support Desk Mgr) | All Tier 1/2 support on the vendor by Aug 1; SLA scorecard live |
| Stand up the TAM seat | Rodney → COO | TAM hired/assigned and running alignment reviews that feed the vCIO |
| FIPS 140-3 migration | vCISO / L4 engineer | All CJIS-path crypto on FIPS 140-3 before Sep 21, 2026 |
| Scope the CMMC client | Rodney (vCISO) | Existing CMMC client assigned; 800-171 Rev 2 gap + POA&M documented (ahead of Nov 10, 2026) |

# Year-by-year roadmap

| Year (illustrative rev.) | Seats to fill | Certifications | Service lines / campaigns | Compliance milestones |
| --- | --- | --- | --- | --- |
| Year 1 — H2'26–H1'27 (~$2.0→$3.0M) | TAM; Support Desk Mgr (Brandon); Design Desk (Centralized Services already filled — Reyes) | Rodney earns CISM + CISSP; CMMC RPO registration + RP; Reyes M365 Enterprise Admin Expert confirmed (SharePoint ready), AIaaS needs AI-102 | Restart NRR (Design Desk); SharePoint-aaS launch (Reyes — cert-ready) | FIPS 140-3; CMMC client POA&M; CJIS baseline; design the offshore access boundary |
| Year 2 — '27–'28 (~$3.0→$4.5M) | 2nd vCIO+TAM pair; Finance/Admin (offload Randy) | CCP (CMMC, via ISACA); TAM CompTIA (Security+/Network+); MS-102 | AIaaS launch + AI University live; Healthcare (HIPAA) campaign | Pursue Securafy's own CMMC L2; CMMC Phase 2 (Nov'26) client certs; HIPAA-aligned offering + BAAs |
| Year 3 — '28–'29 (~$4.5→$6.7M) | Service Delivery Manager (offload Rodney from Ops); 3rd delivery pod | Split vCIO / vCISO into separate seats; CRISC/CISA; CHPS | Website-aaS at scale; CJIS government wins | HITRUST if Healthcare scales; CJIS P2–P4 (auditable Oct'27) |
| Year 4 — '29–'30 (~$6.7→$10M) | Fill remaining target-chart seats; service-line owners | Depth/renewals across the cert portfolio | All five lines mature; three campaigns producing | Sustained multi-framework compliance practice |

# Certification acquisition schedule

| Cert / capability | Who | Target window |
| --- | --- | --- |
| CISM, CISSP | Rodney (vCISO) | Year 1 (P0) — after offload |
| CMMC RPO + RP | Securafy / Rodney | Year 1 (P0) |
| FIPS 140-3, CJIS baseline | vCISO / L4 | Year 1 (P0) — FIPS before Sep 21, 2026 |
| CCP (CMMC, ISACA) | Rodney / engineer | Year 2 (P1) |
| Securafy own CMMC Level 2 | Securafy | Year 2 (P1) — ahead of broad Phase 2 |
| MS-102 (SharePoint-aaS) | Design/CS engineer | Year 2 (P1) |
| CompTIA Security+/Network+ | TAM | Year 2 (P1) |
| Azure AI-102 (AIaaS) | Engineer | Year 3 (P2) |
| CHPS, CRISC/CISA | vCISO track | Year 3 (P2) |
| HITRUST (if Healthcare scales) | Securafy | Year 3–4 (P2) |
| CASP+/PenTest+ depth | L4 engineers | Year 3–4 (P2) |

# Service-line launch sequence (revenue-first)

Core MSP/MSSP + TBR-driven NRR — Year 1. Immediate revenue from the restarted engine; no new build.

SharePoint-aaS — Year 1–2. Clearest cert path (MS-102), fastest to monetize.

AI as a Service + AI University — Year 2. AI University doubles as marketing (Jillian) and a lead engine.

CMMC/CJIS/HIPAA compliance services — Year 2–3. Highest-margin premium; rides the campaigns and the regulatory deadlines.

Website-as-a-Service — Year 2–3. Competency-based; scales with the AI tooling.

# Critical path & dependencies

Everything depends on offloading Rodney first. Until the TAM seat and the Mission Control cutover remove reactive load, Rodney cannot run TBRs or study for CISM/CISSP — so both revenue and the compliance practice stall. This is the single highest-leverage sequence in the plan.

TBRs are the revenue engine. NRR and renewals from TBRs fund Design Desk and Centralized Services, which in turn increase capacity and NRR — a reinforcing loop.

The CMMC clock is external and fixed. The existing CMMC client and the Nov 10, 2026 Phase-2 date don't wait for the org to be ready — the CMMC scoping Rock is Q3 2026 regardless of the rest of the ramp.

The offshore access boundary is a prerequisite for the CJIS/CMMC campaigns. Reyes (Centralized Services) and any offshore/outsourced staff must be walled off from regulated clients, with a US-staffed delivery lane for CJIS/CMMC accounts. Mission Control has confirmed it can supply the US-based, background-checked help-desk staff for that lane (they still need the CJIS Security Addendum + awareness training). Design this control before scaling regulated clients — it is an audit-failing item if bolted on late.

Certs gate the premium revenue. CISM/CISSP + CMMC RPO/CCP are prerequisites to sell the compliance services that carry the best margin — so they're front-loaded into Years 1–2.

# Risks & assumptions

Revenue-gated (primary risk): if revenue lags, hiring slows. Mitigation — the sequence front-loads revenue-generating seats (vCIO/TAM/Design Desk) so the plan funds itself; discretionary hires (2nd pods, SDM) flex with actual revenue.

Key-person dependency on Rodney: he holds vCIO + vCISO to start. Mitigation — document each role separately (done), split the seats in Year 3, and cross-train.

Rodney's bandwidth for certs while transitioning — mitigation: offload is Rock #1.

Compliance deadlines are external (FIPS Sep'26, CMMC Phase 2 Nov'26, CJIS Oct'27) — tracked as fixed dates, not flexible milestones.

The Core MSP plan is aggressive — +$10–15K/mo net-new MRR (vs. current <$6K) and no churn. If the MSP underperforms, Securafy Digital Services must carry a larger share of the $10M — stress-test both divisions in 04-financial-model.xlsx.

Current cert holders unconfirmed — if staff already hold any P0/P1 certs, several items accelerate.