# Securafy — Q3 2026 Company Rocks

EOS Level 10 Meeting · Quarter: July 1 – September 30, 2026

Theme: Stop the leak, turn on the engine, LAND & EXPAND.

Revenue snapshot (live, July 2026):

Managed MRR $101,701/mo + ORR $35,286/mo = $136,987/mo total recurring, across 13 clients.

NRR (project / professional-services labor — excludes product sales) ≈ $0; target 20–30% of MRR ≈ $20–30K/mo.

Net-new MRR added in 2026 = $0.

Pricing is healthy (blended managed AISP $247/seat). The flat-MRR problem is a new-logo + concentration problem (four New Albany accounts ≈ 67% of MRR), not underpricing.

# The Rocks

| # | Rock | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| 1 | Finish the diagnostic sprint | Randy + Rodney | Aug 15 | Partly done (3 of 7) |
| 2 | Restart the TBR / NRR engine + stand up the TAM (#1 priority) | Rodney | Sep 30 | On Track |
| 3 | Mission Control full cutover | Brandon | Aug 1 | On Track |
| 4 | Instrument & run the sales engine — NEW logos | Ric | Sep 30 | On Track |
| 5 | LAND & EXPAND — finish the 5 AI tools | Randy | Sep 30 | On Track |
| 6 | Close out the pricing / small-account assessment | Rodney | Jul 31 | Largely done |

# Rock 1 — Diagnostic sprint (detail)

Done:

✅ AISP-conversion audit — live from AutoTask (13 clients, per-client MRR/seats/AISP).

✅ Revenue-mix split — MRR $101,701 vs ORR $35,286 (product sales tracked separately).

✅ NRR defined — project / professional-services labor; does NOT include product sales.

Remaining:

▢ BDM activity baseline — actual dials / decision-maker conversations / FTAs vs. benchmark (are they dialing?).

▢ Turning-point calc — MRR vs. all operating expenses (excluding product COGS): are we above or below?

▢ Unrealized-profitability calc — (# employees × $150K) − annual MRR: how much profit is trapped in pricing/leverage.

▢ Quantify the NRR gap — current ≈ $0 vs. target 20–30% of MRR ≈ $20–30K/mo.

# Rock 2 — TBR / NRR engine + TAM (the #1 priority)

Done when: the TAM is seated and feeding the vCIO; Technology Business Reviews run on cadence (monthly for larger clients); and NRR is on a run-rate toward 20–30% of MRR (~$20–30K/mo). This is the single highest-leverage move — no TBRs is why NRR is $0.

# Rock 5 — LAND & EXPAND: the 5 AI tools (Randy)

LAND & EXPAND is our backdoor go-to-market: use free AI assessments to get a foot in the door at a prospect, convert them to a client, then move down the stack — vCISO-as-a-Service → Compliance-as-a-Service → MSSP → MSP. It is the engine for new logos (Rock 4) and Securafy Digital Services. Done when all five are live:

BDR-initiated IT/Cybersecurity assessment — BDR marks a HubSpot company+contact → auto-creates it in AutoTask → creates the account in Datto RMM → RMM agents auto-push to the client's systems → Datto pushes the RapidFire Tools agent → scans start.

Domain Name Scan campaign (email security) — HubSpot campaign using the Advanced Domain Name Scanner; email the report to prospects who fail or score ≤ 7, with a landing page for a free 30-min consult + a 12-month domain management & monitoring offer.

Website report campaign — AI scores SEO, AEO, Security, and Performance; anyone with a C/D/F in any category gets a full report + free-consult link + a discounted rewrite/monitor/manage offer.

SharePoint assessment campaign — AI SharePoint report card, same report-card → consult → offer flow.

M365 SecureScore campaign — AI SecureScore report card, same flow → appointment + opportunity.

# Rock 6 — Pricing / small-account assessment (findings — largely complete)

Pricing is healthy — blended managed AISP $247/seat (in the world-class $150–250 band). Not underpriced; no repricing needed.

The four sub-$1,800/mo accounts do not consume vCIO/TAM time (by their own request).

Friendsville Sand, Supro Spring, and Walford are owner-remnants of former LARGE clients that closed or sold — the owners asked to keep their systems protected only. Not upgrade targets; leave as protection-only.

KASS Corporation is the only possible (small) upgrade candidate.

Action: no repricing; monitor KASS; leave the remnants as-is. → Rock effectively complete.

# Compliance tasks (tracked, not Rocks) — vCISO / Rodney

FIPS 140-3 migration before Sep 21, 2026 (CJIS). • CMMC client scoping ahead of the Nov 10, 2026 Phase-2 date.

# The MRR math to manage

New MRR = FTAs × Close Ratio × Average MRR — targets: 15–20% close · $3,500 avg MRR · ~2 FTAs/week per rep. Track weekly: FTAs, close ratio, avg MRR of closed deals, pipeline (30-day / 31–60-day), net-new MRR, NRR as % of MRR.

# Leadership team & seats

Randy — Visionary / CEO + head of Securafy Digital Services (LAND & EXPAND)

Rodney — Integrator / COO + vCIO/vCISO (transitioning as revenue funds the split)

Ric — CRO · Jillian — CMO · Brandon — Support Desk Mgr · Reyes — Centralized Services / SharePoint lead

# L10 discipline

Rocks reviewed weekly — On Track / Off Track (binary). Off-Track → IDS. Quarter-end: Done / Not Done, 90% completion standard.